## To do
Event Planning Checklist
1/36 completed
✓ | Date | Task
TRUE | 2026-04-08 | Define event goals and objectives (purpose, KPIs, success definition)
FALSE | 2026-04-08 | Identify your target audience (personas, segments, value proposition)
FALSE | 2026-04-09 | Sort items using the drop-down arrows next to the heading name (on the web)
FALSE | 2026-04-10 | Create Event budget (with contingency)
FALSE | 2026-04-10 | Set Event date and time (avoid major conflicts, audience-first timing)
FALSE | 2026-04-10 | Governance and work cadence
FALSE | 2026-04-22 | Select and contract your venue
FALSE | 2026-04-22 | Permits, insurance and compliance
FALSE | 2026-04-22 | Core vendors (e.g. AV production, F&B, Photography)
FALSE | 2026-04-22 | Floorplans, traffic & signage
FALSE | 2026-04-29 | Ticketing setup (event page, types, tiers, promotions)
FALSE | 2026-04-29 | Registration workflow
FALSE | 2026-04-29 | Attendee care & hospitality
FALSE | 2026-04-29 | Owned Channels (website, email, blog)
FALSE | 2026-04-29 | Paid & Earned media (Paid search, influencers, PR)
FALSE | 2026-05-06 | Social Plan (Calendar, engagement, live coverage)
FALSE | 2026-05-06 | Packaging & pricing (Inventory, tiers, prospectus)
FALSE | 2026-05-06 | Sales ops (contracts, deliverables, invoicing)
FALSE | 2026-05-06 | Exhibitor operations (manual, lead capture, move-in / move-out)
FALSE | 2026-05-13 | Organisation chart & roles
FALSE | 2026-05-13 | Recruitment & onboarding (Job description, training, briefing)
FALSE | 2026-05-14 | Select your event tech stack
FALSE | 2026-05-15 | Integrate systems & data flows
FALSE | 2026-05-16 | Wi-Fi, connectivity & network planning
FALSE | 2026-05-17 | Pre-event testing & QA
FALSE | 2026-05-18 | Backup & contingency protocols
FALSE | 2026-05-19 | Load-in & load-out scheduling
FALSE | 2026-05-20 | Daily venue setup & resets
FALSE | 2026-05-21 | Stage management & show calling
FALSE | 2026-05-22 | Crowd management & attendee flow
FALSE | 2026-05-23 | Vendor, sponsor & exhibitor support
FALSE | 2026-05-24 | Emergency action plan (EAP)
FALSE | 2026-05-25 | Medical & security planning
FALSE | 2026-05-26 | Weather & environmental planning
FALSE | 2026-05-27 | Crowd density & line management
FALSE | 2026-05-28 | Cybersecurity & fraud prevention
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE